## Sheet1
Task Name | Start Date | End Date | Duration
PHASE 1: EDUCATE AND BUILD | 2025-10-01 | 2025-10-15 | 14
Why we're moving to FastPass | 2025-10-01 | 2025-10-04 | 3
Launch Awareness Campaign | 2025-10-04 | 2025-10-08 | 4
email to inform your organization | 2025-10-08 | 2025-10-14 | 6
Prepare the IT support team | 2025-10-14 | 2025-10-15 | 1
PHASE 2: RUN THE PILOT | 2025-10-15 | 2025-11-30 | 46
Send email to pilot groups | 2025-10-15 | 2025-10-17 | 2
Gather feedback | 2025-10-23 | 2025-10-25 | 2
Refine material | 2025-10-26 | 2025-11-15 | 20
Draft FAQs | 2025-10-26 | 2025-11-30 | 35
Support team is prepped to handle calls from end users | 2025-10-26 | 2025-11-30 | 35
PHASE 3: ROLLOUT OKTA FASTPASS | 2025-11-30 | 2025-12-31 | 31
Begin Okta Fastpass rollout | 2025-11-30 | 2025-12-15 | 15
Begin messaging other MFA factor deprication | 2025-11-30 | 2025-12-31 | 31
PHASE 4: ENFORCEMENT | 2025-12-31 | 2026-02-28 | 59
Send final reminders of MFA deprication | 2025-12-31 | 2026-01-15 | 15
Prepare for Support call spike | 2026-01-01 | 2026-02-01 | 31
Assess adoption and support impact | 2026-02-01 | 2026-02-28 | 27
| 45931 | 46081
Read me:
This simplified Gantt Chart and project plan are available for use as a template. Since the chart only supports number fields, the date conversion into numbers is required in cells B20 and C20. The begin date is B20 and the end date is C20, which will update the chart horizonal axis dates.