## Active
Category | Item | Target Date | Status | Next Steps
Portal | Purolator Okta for MxDR Authentication | TBD | In Progress | Coordinating with MxDR PM team (Purolator team experiencing login errors)
Onboarding | AWS Onboarding | TBD | In Progress | Awaiting configuration of Security Hub
Onboarding | New Purolator CrowdStrike Instance | TBD | In Progress | Arvin to trigger test alerts for confirmation
Onboarding | New Proofpoint Tenant (TAP & Email Protection) | TBD | Completed | Logs flowing & triggering alerts - Purolator to review logs and confirm if there are any concerns
Cases | Sharepoint Cases | TBD | Completed | Tuning implemented and case volume decreased - will re-open if additional tuning needed
Portal | User Access/Case Notification | TBD | In Progress | Purolator team to confirm users that need access to Canada Post instance and if/when IT Operations DL can be removed from Canada Post instance (team is receiving case notifications)
Onboarding | Response Actions | TBD | Not Started | Andrea sent response action/enrichment capabilities for Azure AD - Purolator team to review and confirm once ready to proceed
Onboarding | Zscaler | TBD | Completed | MxDR confirmed parsing issue resolved
Portal | Training | Q1 2026 | Not Started | Purolator would like a training session to better understand portal, SIEM, & SOAR (and overall concerns with understanding rules)
Service | Overview of Service | 2026-01-01 | In Progress | Initial call completed on 1/20; Confirmed that Nxlog agent would be required for Windows logging from laptops (but need to review from entitlement perspective)

## Archived
Category | Item | Target Date | Status | Next Steps
Cases | Sharepoint Use Cases | 2025-06-20 | Completed | MxDR implementing additional 16 requested use cases
Onboarding | Stand-alone Purolator Org Setup | 2025-06-20 | Completed | MxDR troubleshooting error with Okta feed
Cases | Escalation Procedures | 2025-06-20 | Completed | MxDR implemented separate procedures for escalated Purolator cases (under Purolator org)
Logging | Telus Cisco ISE - Cert Issue | 2025-07-18 | Completed | Telus disabled cert check
Portal | New User Set Up | 2025-07-15 | Completed | Andrea to create portal accounts for Arvin & Kiran
Onboarding | Cyberhub - Cloud VMs | TBD | Closed | Confirmed Cyberhubs not required for AWS technologies that will be onboarded
Portal | Purolator CrowdStrike Client ID | 2025-08-04 | Closed | Link to new CrowdStrike dashboard provided